## Slide 1
Elizabeth Sterner
Cari Didion
Governors State University
Presented at the 2022 HSLI Annual Conference, September 7, 2022
Weeding the entire library collection: Lessons learned

## Slide 2
Weeding the entire library collection
Background
Steps taken
  Initial organization of systemic processes
  Progress
Challenges faced
Lessons learned

## Slide 3
Governors State University
Mid-size university
Very diverse student population
Founded in 1969
Offering 85 different programs
https://www.govst.edu/about/

## Slide 4
Background
Weeding
Monumental project
  Total collection size before project 1,251,022
  Of that, books and government documents – 254,934
New interim dean

## Slide 5
Initial organization of systemic processes
A – General Works.
L – Education.
Q – Science.
U – Military Science.
R – Medicine.
Z – Bibliography. Library Science. Information Resources.
Determined sections by liaison areas

## Slide 6
Workflow
Public Services Librarian
Shared lists of collections with appropriate faculty librarians
Faculty Librarians
Reviewed lists and made recommendations
Shared recommendations with teaching faculty
Public Services Librarian
Shared final lists with staff and student workers for physical removal
Determined disposal options

## Slide 7
Progress
Rs (medical book collection)
  Weeded the previous year
  12,000 volumes down to approximately 3,000
Qs (science collection)
  Weeded the previous year
  12,300 volumes down to 2,300
Photo taken by Elizabeth Sterner, 4/4/2022
R’s before deselection initiated

## Slide 8
Progress
Photo taken by Elizabeth Sterner, 6/27/2022
HV’s after deselection

## Slide 9
Progress
Photo taken by Elizabeth Sterner, 8/1/2022 After deselection
Photo taken by Elizabeth Sterner, 6/29/2022 After deselection

## Slide 10
Challenges faced
Maintain consistency
  Create deselection criteria
  Make data driven decisions
  Check consistently for Resources for College Libraries (RCL) recommendations
  Include teaching faculty
Determine priorities
  Purchase new materials
  Continue weeding
  Begin shifting

## Slide 11
Lessons learned
• Maintain an effective workflow and professional communication
  Map out a workflow
  Clearly communicate the workflow
  Maintain consistent communication
  Follow created workflows and processes

## Slide 12
Lessons learned
Set realistic goals
  Allow appropriate timeframes to weed
  Consider electronic resources
  Avoid arbitrary deadlines
Maintain morale
  Maintain consistent priorities
  Be considerate of burnout amongst faculty, staff, and student workers

## Slide 13
Elizabeth Sterner
Health and Human Services Librarian
Assistant Professor
Governors State University
www.govst.edu/library
esterner@govst.edu
Thank you!
Cari Didion
Education/Science Librarian
Assistant Professor
Governors State University
www.govst.edu/library
cdidion@govst.edu